## Prioritized
| Project | Currently Assigned | Proposed Assigned | Expected Completion (Quarter) | Priority | OP1 or Related | Quarter Due | OP1 Due | Period Start | eriod End | Notes
1 | FC Site Summary | Arun | Arun/CW | Sadie | 1 | Related | Q1 | P6 |  | P2 | Change of requirements from FC Leads - moderate rework needed
| OpenBark | Shannon | Shannon | Nicole | 1 | Related | Q1 | P6 |  | P1 | Near completion
| Hub Vitality - Volume of Multiple Visits per week | N/A | CW1 |  |  | Related | Q1 |  | P2 | P2 | Medium LOE
| CS Analytics Enhancements (annualized attr, etc) | Shannon | Shannon |  |  | No | Q1 |  | P2 | P2 | Low LOE
-5 | Monthly C-Suite Packets; Including Scott Anderson Reporting; Including CS; Including Ad-Hoc Attrition Tool | N/A | CW1 | Nicole/Sadie | 1 | Related | Q1 | P6 | P2 | P3 | High LOE |  | Get MLP for what the LnD team needs
| Eagle Eye Rework | N/A | David | Alexis |  | Related | Q1 |  | P2 | P3 | Medium LOE |  | Get MLP for what the team needs
2 | Pharmacy Site Summary | N/A | CW1 | Sadie | 2 | No | Q1 |  | P2 | P3 | Medium - High LOE
| MBR Page 0 | N/A | CW | Nicole | 3 | Related | Q1 | P6 | P3 | P4 | Medium - High LOE |  | Get MLP for what the team needs
4 | OTMP Dashboard | N/A | CW1 | Sadie | 3 | Related | Q2 | P6 | P2 | P4 | High LOE
5 | FC Retention WBR/MBR | N/A | CW2 | Sadie | 4 | Related | Q2 | P6 | P2 | P3 | Medium LOE
3 | FC Talent Management | N/A | CW1 | Sadie | 4 | Related | Q2 | P6 | P3 | P4 | High LOE |  | Get MLP for what the team needs
| LnD | N/A | CW2 | Nicole | 1 | Yes | Q2 |  |  |  | Medium LOE |  | Tech spec
| Strategic Talent Plan | N/A | CW2 | Nicole | 2 | Yes | Q1 | P6 | P2 | P3 | Medium - High LOE
| DEI Enhancements | N/A | Arun | Nicole |  | Yes | Q1 | P4 | P2 | P3 | Low LOE
| Employer Branding Dashboard | N/A | CW | Nicole |  | Yes | Q2 | P4 |  |  | ????
| Leave of Absence | N/A |  | Nicole | 4 | No | Q2 |  |  |  | Low LOE | Vendor change is OP1, not reporting | Get MLP for what the team needs
| CS WBR | David | David | Nicole | 6 | No | Q1 |  |  |  | Low LOE | Work has started - Low LOE
| CS HRBP | N/A |  | Nicole | 5 | No | Q2 |  |  |  | Low LOE
| C-Suite Spans and Layers | N/A |  | Nicole | 6 | Yes | Q2 | P6 |  |  | Medium-High LOE
| Hub Vitality - Representation of data (Events) |  | CW |  |  | Yes | Q2 | P4 |  |  | Low LOE
| Pharmacy Staffing | [11 empty] | Get MLP
| Support Site Summary | [11 empty] | Needs scoped
Rationalized
Eagle Eye
PAWS/HRBP
Brass Tacks
AA
6 | Performance Management? -- Corrective Actions
7 | Day 1 and 14 Reporting